## Sheet1
WORKSHEET 6 - STATUS OF PAST PROJECTS
JURISDICTION: Village of Hoosick Falls
Name and Title: Niel Stowell
Email and Phone: Nielstowellhighway@gmail.com
First: | Before you begin, please provide a General Overview of how local priorities have changed since the last version of the plan: Increase storm water has maxed out existing storm water infrastructure
Initiative #, 2011 | Mitigation Initiative Description | Previous Priority | Hazard(s) Mitigated | Lead and Support Agencies | Status - Check One |  |  |  | Status Details | Relevance - Check One |  | Relevance Details
[5 empty] | Completed | Initiated but Not Completed | Ongoing Type of Activity | Not Initiated | If not completed, identify barriers to implementation (i.e., lack of political support, funding, staff availability, etc.) or explain why the action is an ongoing one (i.e., acquisition of hazard prone land for open space can be completed for a given parcel or group of parcels, but there may be many more opportunities in the community and so the activity may be carried forward) | Still Relevant - Carry Forward to Updated Mitigation Strategy | No Longer Relevant - Omit from Updated Mitigation Strategy | If you checked the box that the project is being carried forward to the updated mitigation strategy, describe if and how it has changed from the 2011 Plan. If you checked the box that the project is being omitted from the updated mitigation strategy, provide a brief explanation.
HF-1 | #1 Wood Brook project in the Village of Hoosick Falls is a high priority structural project to implement improvements to channels, drainage and floodwalls. Benefits in every category except social as it would be targeting one section of the community but most community members would agree it is a much needed project as the current infrastructure needs to be improved to stop flooding. The cost would be substantial as outside consultants and engineers would need to be brought in to identify the much needed improvements therefore funding would be needed to do the project. | High 1 | Flooding | Board of Trustees, Highway Department |  | ü |  |  | 2 projects in program NYS CDGB project ID 546PR31-17 & NYS Housing Trust Fund CORP SHARS # 20180126 | ü |  | Work has begun
HF-2 | #2 Zoning and Building code improvement and updating is a high priority project for the Village of Hoosick Falls as the Village is dealing with old buildings that need to be assessed for health and safety issues. This project would be one that could identify and do a study on buildings that have been abandoned or that need to be updated or demolished by the current owner. This project would benefit the community in every category except specific legal issues that would have to be dealt with. Outside consulting would have to be brought in to help with legal guidelines and implementation of the project. | High 2 | All | Building Codes Department |  | ü |  |  | Large number of vacant buildings | ü |  | We now have a full time Code Officer
HF-3 | #3 Grant funding to help update the public information activities in the Village. A project to build a web-site for the Village where a wide variety of information would be provided for the community. The Village is doing away with their dispatch department which has served as an informational and emergency center for the community. It is imperative that we provide the community with the ability to find out information especially in regard to potential emergency situations. This would be a great project with benefits in every category. | High 3 | All | Board of Trustees, Highway Department | ü |  |  |  | We now have new village webiste |  | ü | We have new website, Rensselaer County now dispatched, 911 coming soon
HF-CL-1 | Public awareness program on Hazards, Prevention, and Mitigation: County will maintain a hazard mitigation and mitigation planning web presence (local municipal web sites to link up to this site, if they haven’t already done so); all participating jurisdictions to support preparation of a joint annual hazard mitigation and mitigation planning fact sheet and its distribution; periodic discussion of hazard mitigation and the mitigation plan at other regular local meetings; use of annual flyers, newsletters, advertisements, or radio/tv announcements, etc. at the discretion of each jurisdiction (incorporating as much free information as possible from the FEMA Publications Warehouse and other appropriate sources). (public education) | High | All hazards | County-led action item. CPG Member, Village Trustee, |  |  | x |  | Insert a summary of outreach your municipality undertoook from 2011-2018, see cell B14 or anything else you may have done along those lines. | x |  | County is carrying forward this County-led activity with no changes; our municipality will it carry it forward as well.
HF-CL-2 | Code update: Review existing local codes and ordinances against the identified hazards to determine whether there need to be any amendments to address identified hazards and, where a need is identified, modify/amend the codes/ordinances as applicable. (prevention) | Medium | All hazards | County-led action item. CPG Member, Village Trustee |  |  | x |  | Either (a) specify what codes/ordinances were modified, and whether or not the County provided support during this modification; or (b) state that 'a need was not identified to modify/amend any local codes/ordinances.' | x |  | County is carrying forward this County-led activity with no changes; our municipality will it carry it forward as well.
HF-CL-3 | Code enforcement: Enforcement of NYS and Local Building Codes with Continual CEO training. (prevention) | Medium | All hazards | County-led action item. CPG Member, Village Trustee |  |  | x |  | Locally administered on an ongoing basis; our community (did/did not) have a need to go to the county for support/training. | x |  | County is carrying forward this County-led activity with no changes; our municipality will it carry it forward as well.
HF-CL-4 | Ensure that local comprehensive plans incorporate natural disaster mitigation techniques through a courtesy review of draft plans by the County Planning Department (prevention) | High | All hazards | County-led action item. CPG Member, Village Trustee |  |  | x |  | Say whether your community has a comprehensive plan (master plan). If so, (1) say whether it was revised to incorporate natural disaster mitigation techniques, and (2) whether or not the revision was routed through County Planning. | x |  | County is carrying forward this County-led activity with no changes; our municipality will it carry it forward as well.
HF-CL-5 | Hold periodic workshops for municipalities regarding zoning and planning issues that arise regarding natural hazards and hazard mitigation. (prevention) | Low | All hazards | County-led action item. CPG Member, Village Trustee |  |  | x |  | County- led activity. Municipality attends meetings/workshops as offered by the County whenever municipal staff members have schedule availability. | x |  | County is carrying forward this County-led activity with no changes; our municipality will it carry it forward as well.
HF-NFIP-1 | Update/revise floodplain management ordinance to comply with latest FEMA regulations. | Medium | Flooding | Village Board |  |  | x |  | Ordinance was updated in 2017. | x |  | Ongoing type of activity; will be carried forward with no changes.
HF-NFIP-3 | Add/train sufficient members of staff to adequately enforce NFIP regulations/floodplain management ordinances. | Medium | Flooding | Highway Department |  |  | x |  |  | x |  | Ongoing type of activity (with staffing changes); will be carried forward with no changes.
HF-NFIP-4 | Update/revise flodplain management ordinance to be consistent with potential future new FIRMs | Medium | Flooding | Village Board |  |  | x |  | Ordinance was updated in 2017; new maps issued in 2016. | x |  | Ongoing type of activity; will be carried forward with no changes.
HF-NFIP-5 | Require staff involved in floodplain management and ordinance enforcement to become Certified Floodplain Managers (CFMs) | Medium | Flooding | Highway Department, Building Inspector |  |  |  | x | Not agency required; municipality opted not to require CFM certification.
HF-NFIP-6 | Join the Community Rating System (CRS) | Medium | Flooding | Village Board |  |  |  | x | Municipality opted not to enter CRS. | x |  | Municipality intends to explore further during next planning cycle; carrying forward with no changes
** NYSDHSES requires the documentation of local mitigation efforts and accomplishments within the past five years, regardless of inclusion in the previous plan, and regardless of funding source. The goal is to provide a context for the jurisdictions projects act as a source of ideas for mitigation projects and evaluate the accuracy of assumptions and engineering solutions to inform future projects, and to support future mitigation plannng and its coordination with other planning, zoning and environmental procedures within the jurisdiction. Please fill in the following table to convey this information.
Past Mitigation Accomplishments - Village of Hoosick Falls
Project Number | Project Name | Hazard(s) Addressed | Brief Summary of the Original Proglem and the Solution (Project) |  | Evaluation of Success
HF 1 | Woods Brook | Flooding | Extensive & repeated flooding in middle of village. Removing houses |  | Cost |  |  |  | 1100000
[5 empty] | Level of Protection |  |  |  | High
[5 empty] | Damages Avoided; Evidence of Success |  |  |  | Repeated flood damage
HF 2 | Zoning & Building Code Improvement | All | Health & Safety issues of old & vacant buildings use codes to improve buildings in worse condition |  | Cost
Level of Protection
Damages Avoided; Evidence of Success
HF 3 | Public Information | All | Local informaiton always been available through local dispatcher which has been discontinued, new web site was set up |  | Cost |  |  |  | 10000
[5 empty] | Level of Protection |  |  |  | Med
Damages Avoided; Evidence of Success
Cost
Level of Protection
Damages Avoided; Evidence of Success
Cost
Level of Protection
Damages Avoided; Evidence of Success
Please insert additional rows for more projects if needed